### Policy Researchers

Days 1–30

- Identify 3–5 priority governance themes (e.g., budget transparency, access to information, digital ID, elections, protests).

- Create research templates and citation standards.

- Conduct literature review.

- Publish one brief explainer per focus area.

- Map existing African policy data.

Days 31–60

- Produce one policy memo and one comparative snapshot

- Collaborate with Data Scientists to analyze datasets and with Comms on summaries.

- Engage with the Tech & Dev team to align tools with policy needs.

- Begin outreach to reviewers or academic partners.

Days 61–90

- Co-author whitepaper with insights from data + policy.

- Host a public webinar or roundtable on findings.

- Publish open access policy research repo.

- Propose next-quarter research agenda tied to advocacy.

Dependencies

- Data for evidence; Comms for dissemination; Partnerships for uptake.